## Sheet1
# | Data Conversion Step
1 | Extract, Cleanse, Validate Data and Receive Signoff from Client
2 | Extract Cross Reference (XREF) details [manually prepared]
3 | Stage the source data
4 | Populate Cross Reference details to XREF Tables
5 | Populate/ Synchronize XREF/ Pre-validation data (Master Data/ Setup Data) from Fusion to XREF Tables either by invoking Report Service or Schedule Service
6 | Populate the already processed/imported data in the cloud for the object concerned. Note – Only the current run is delta load or next iteration. If the current load is fresh mock, then no need to populate.
7 | Pre-validate the source data
8 | Generate Error Report post pre-validation. To be referred for correcting data concerned for migration or dependent data or setup data
9 | Configure Transformation rules
10 | Transform the clean data post pre-validation
11 | Prepare the data
12 | Load/ Import data into Oracle ERP Cloud
13 | Generate Reconciliation Report post import
14 | Reconcile the imported data with the extracted data at source
15 | Update the scorecard in order for all stake holders to view and analyze
16 | Send Email (Optional) to all the stake holders